## Summary
AAIS Technical Review — Tracker Summary
Live counts driven by the other sheets. Update Status columns there; this page recalculates.
Issues by severity | Count | Open | Done
Critical | 3 | 3 | 0
High* | 5 | 5 | 0
Medium* | 10 | 10 | 0
Low* | 4 | 4 | 0
Total issues | 22 | 22 | 0
Backlog by priority | Tickets | Open | Done
P0 | 7 | 7 | 0
P1 | 7 | 7 | 0
P2 | 8 | 8 | 0
P3 | 3 | 3 | 0
Readiness checklist | Items | TODO | Done
All categories | 29 | 29 | 0
Top 3 actions this week
1. Rotate every key in 'All API Keys.docx', then delete it (T-01).
2. Disable Bobie/Phoebe demo logins in production (T-02).
3. Push the repository to a private GitHub with protected main (T-03).

## Issues Register
AAIS Issues Register (ranked by severity, then urgency)
AAIS Technical Review — July 8, 2026 · companion to AAIS-Technical-Review-Report.docx
ID | Issue | Area | Severity | Evidence / symptom | Why it matters | Risk if ignored | Recommended fix | Effort | Suggested owner | Priority (3-mo) | Status
ISS-01 | Hardcoded demo accounts active in production (Bobie/Phoebe, password 12345) | Security / Auth | Critical | src/lib/server/aais-trial-accounts.ts lines 45–58 define built-in accounts with password '12345'; mergeConfiguredAccountsWithBuiltInLearners() always prepends them to configured production accounts. Login confirmed working on www.aais.site. | These credentials are effectively public (shared in docs/conversations). Anyone can enter the platform as a student. | Strangers write junk learner data, consume paid AI tokens, and any future real-student data is exposed; reputational damage with pilot schools. | Gate built-in accounts to non-production builds; rotate every configured trial password to strong generated values; redeploy; verify old login fails. | S | Junior dev | Week 1 | Open
ISS-02 | No git remote — source code exists only on one laptop; CI never runs | DevOps / Workflow | Critical | `git remote -v` is empty; single branch codex/aais-enterprise-standard; .github/workflows/ci.yml triggers on main/PRs, which do not exist. | The production site's source has no backup and no review/quality gate. | Laptop loss, failure, or theft permanently destroys source history; deploys remain unauditable. | Create private GitHub repo; push full history; protect main; connect Vercel Git integration; verify CI green on a test PR. | S | Junior dev | Week 1 | Open
ISS-03 | Plaintext credentials file 'All API Keys.docx' in the project folder | Security / Secrets | Critical | 16KB docx at repo root containing sk-style keys and passwords (DeepSeek, SimpleTex, Mathpix, Resend, more). agents.md explicitly sanctions the file for AI-assisted work. | A single sync, backup, screen-share, or tool upload leaks every provider credential at once. | Provider abuse billed to the owner; account takeovers; forced emergency rotation later under worse conditions. | Move all secrets to a password manager; rotate every key present in the file at each provider; delete the file; update agents.md guidance. | S | Product owner + junior | Week 1 | Open
ISS-04 | Learner state stored as one JSONB blob per student; concurrent writes lose data | Data model | High | Table aais_learner_sessions(student_id PK, payload jsonb); every action does read-modify-write of the whole blob (aais-learning-store.ts writeSession); no version check or locking; events array grows without bound. | Autosave + AI chat + a second tab run concurrently in normal use; last write wins over the entire learner history. | Silent loss of student work and evidence events; rows grow to MBs; analytics and exports degrade then fail. | Interim (Weeks 3–4): version column + compare-and-swap with retry. Month 2: move events to append-only aais_events table + slim learner_task_state snapshot; backfill; dual-read one release. | M | Senior (design) + junior (impl) | Weeks 2–6 | Open
ISS-05 | No staging environment; no schema migration tooling | DevOps / Data | High | Only production in .vercel/project.json; CREATE TABLE IF NOT EXISTS executed at runtime; restore rehearsal is a manual runbook procedure. | Every schema or code change is first tested on live users; restores are untested under pressure. | A bad deploy or migration corrupts production data with no rehearsed recovery. | Vercel preview env + seeded Neon branch as staging; adopt node-pg-migrate (or equal); migration 001 formalizes existing tables; delete runtime DDL. | M | Junior dev (senior review) | Weeks 2–4 | Open
ISS-06 | Public /api/system/readiness endpoint discloses internals | Security / API | Medium | Live fetch on 2026-07-08 returned release id, deployment git SHA, storage provider, trial account count, LRS outbox metrics, AI timeout/token config, and admin endpoint paths — no auth required. | Hands an attacker a map of the system; combined with ISS-01 it is a guided tour. | Easier targeted attacks; information leakage grows as the report grows. | Public GET returns bare {status}; full report requires admin session or bearer token. | S | Junior dev | Weeks 1–2 | Open
ISS-07 | Login rate limiting is in-memory — ineffective on serverless | Security / Auth | Medium | aais-auth-rate-limit.ts keeps a Map in module scope; Vercel serverless instances neither share memory nor persist between invocations. | The documented '5 failures = 15-min lock' protection does not actually hold in production. | Practical brute-force/credential-stuffing against static passwords (worsened by ISS-01/ISS-08). | Move counters to Postgres or Upstash Redis keyed by account+IP; optionally add platform WAF rate rules. | S–M | Junior dev | Month 2 | Open
ISS-08 | No real user model (no registration, invites, password reset, user table) | Product / Auth | High | Accounts exist only in AAIS_TRIAL_ACCOUNTS_JSON env var; changing a password requires a redeploy; teachers/admins use static credentials; OIDC exists in code but is unconfigured (live readiness: oidc.mode=missing). | Cannot onboard a real class; no self-service recovery; admin/teacher compromise is likely and unauditable per person. | The product cannot leave demo stage; every user operation becomes a developer task. | users table + invite-based registration + password reset via Resend (key already owned); individual staff accounts; keep OIDC optional for institutions. | L | Senior + junior | Month 2 | Open
ISS-09 | Frontend monolith: learning-page.tsx is 2,269 lines with 21 useState hooks | Code quality | High | Single client component contains chat, editor, task list, attachments, autosave, export, and navigation; 4 fetch call sites; no extracted API client. | No new developer can safely change one feature; component-level testing is impossible. | Every UI change risks regressions across all flows; velocity collapses as features are added. | Extract a typed API client; split into ~6 feature components + custom hooks; incremental, behavior-preserving, protected by E2E tests. | M | Junior dev (senior review) | Month 2 | Open
ISS-10 | Release-evidence machinery outweighs the product and fails its own gate | Codebase / Process | Medium | 22 scripts in scripts/, ~20 test files for them, 64KB README of ceremony commands; output/aais-enterprise-release-check-latest.json (2026-07-01) shows status=failed on all 5 steps while production ships anyway. | Maintenance drag and false confidence; the ceremony is treated as optional, so it protects nothing while consuming attention. | New engineers are intimidated/misled; real quality signals stay buried; CI time wasted. | Archive to tools/release-legacy (kept in git history); keep one smoke:prod script + a one-page release checklist. | S | Junior dev | Weeks 3–4 | Open
ISS-11 | LangGraph claimed but never used; misleading runtime labels | Codebase / Honesty | Low–Medium | @langchain/langgraph in dependencies with zero imports anywhere in src; orchestration is Promise.all; API responses report engine 'aais-langgraph-runtime' and runtime 'langgraph'. | Misleads future engineers, stakeholders, and any technical due-diligence. | Wasted debugging of a framework that isn't there; credibility damage when discovered externally. | Remove the dependency; rename labels to something honest (e.g., aais-orchestrator-v1); or actually adopt LangGraph when a real graph exists. | S | Junior dev | Weeks 3–4 | Open
ISS-12 | AI layer overstates itself (A3/A4 canned; 180-token cap; 0 retries; silent fallback) | Product / AI | Medium | aais-learning-guide-graph.ts always assigns A3/A4 the deterministic template provider; live readiness shows maxTokens:180, maxRetries:0; provider failure silently returns template text presented as agent output. | Students receive truncated or canned guidance while the product claims adaptive multi-agent AI; teachers can't tell live from fallback. | Pedagogical claims become indefensible; user trust erodes when the gap is noticed. | Product owner defines the honest scope; raise token budget (~600) and add 1 retry; label fallback/template responses in the UI; consider one contextual model call instead of the fan-out. | M | Product owner + senior | Months 2–3 | Open
ISS-13 | No error tracking, alerting, or uptime monitoring | Observability | Medium | Only console.info JSON audit lines into Vercel logs; no Sentry/equivalent; no uptime checks; cron flush failures invisible. | Production breakage is discovered by users; diagnosis means scrolling function logs. | Longer outages, lost pilot goodwill, undiagnosable intermittent bugs. | Add Sentry (client+server) with release tags; uptime monitor on /login; alert on cron failure and error-rate spikes. | S | Junior dev | Weeks 1–2 | Open
ISS-14 | No end-to-end tests of real user flows | Testing | Medium | 44 Vitest files, roughly half covering release scripts; component tests exist, but no browser E2E specs in the repo (.playwright-cli is only a tool cache). | The Month-2 refactors (data layer, frontend split) have no behavioral safety net. | Refactors silently break login/learning/dashboard; regressions ship. | 6–8 Playwright specs: login ok/fail, task flow + persistence, AI guide + labeled fallback, dashboard access control, export; run in CI against preview deploys. | M | Junior dev | Month 2 (start Wk 3–4) | Open
ISS-15 | Cohort analytics loads every learner blob into memory per request | Performance | Medium→High | getCohortAnalytics() calls readAllSessions() (SELECT all payloads) then aggregates in JS on every dashboard request. | Cost grows linearly with students × per-student history; serverless memory/time limits are fixed. | At a few hundred active students: multi-second dashboards, then OOM/timeouts; export breaks first. | After ISS-04: compute aggregates in SQL over aais_events with proper indexes; paginate learner drill-down. | M | Senior engineer | Months 2–3 | Open
ISS-16 | Education-privacy baseline missing (consent, retention, deletion, DPAs) | Privacy / Compliance | High (gates real users) | /privacy page exists, but there is no per-user export/delete, no retention policy, no data inventory; Neon/LRS data-processing terms and regions unverified; audience likely includes minors. | Education data is regulated (FERPA/COPPA/GDPR/PIPL depending on region); schools will ask and there is no answer. | Legal exposure; pilot rejections; emergency compliance work later at 10x cost. | Data inventory; retention policy; per-user export + delete endpoints; consent flow for minors; confirm Neon/LRS DPAs and regions. Must complete before any real cohort. | M | Product owner + senior | Month 3 (gate) | Open
ISS-17 | Sessions not revocable server-side; logout only clears the cookie | Security / Auth | Low–Medium | Stateless HMAC token remains valid for its full 8h TTL regardless of logout; no denylist or session table. | A leaked/stolen token cannot be killed. | Extended unauthorized access after a compromise; no forced-logout capability. | Acceptable short-term; later add session ids + denylist or DB-backed sessions; rotate the session secret to invalidate everything if needed. | S | Senior engineer | Month 3 | Open
ISS-18 | CSP allows unsafe-inline and unsafe-eval | Security / Headers | Low | next.config.ts sets script-src 'self' 'unsafe-inline' 'unsafe-eval'. | Weakens the main mitigation against XSS. | Any XSS foothold escalates more easily. | Move to nonce-based CSP; drop unsafe-eval for production builds. | S | Senior engineer | Month 3 | Open
ISS-19 | Accessibility and responsiveness gaps | Frontend / UX | Medium | globals.css is 120 lines with a single @media query; aria attribute counts: learning 51, login 4, teacher dashboard 1; desktop-oriented cockpit layout. | Phone-first students and assistive-tech users are excluded; schools often have accessibility requirements. | Pilot users bounce on mobile; procurement blockers later. | axe + keyboard audit; fix top violations on the 3 core screens; explicitly state the mobile policy (support it or message it). | M | Designer + junior dev | Month 3 | Open
ISS-20 | Documentation unusable for onboarding | Docs / Workflow | Medium | README.md is 64KB (274 very long lines) of enterprise release commands; no setup guide beyond npm ci; agents.md describes a fictional 11-role team; single ops runbook is release-ceremony-centric. | A new engineer cannot get productive without the original author. | Bus factor stays 1; every hire burns days; knowledge stays trapped. | Rewrite docs set: 1-page README, ARCHITECTURE.md, OPERATIONS.md (deploy/rollback/restore), CONTRIBUTING.md; archive the old README. | S | Junior dev | Weeks 3–4 | Open
ISS-21 | Fake streaming: SSE buffers the whole AI response, then replays it | Backend / UX | Medium | createGuideStreamResponse() awaits the full multi-agent run before emitting SSE events; with a 30s provider timeout students may wait ~30s with no output. | Perceived as broken; students abandon the guide mid-task. | Core feature feels unreliable; support burden. | Stream provider tokens through, or send honest staged progress events + timeout messaging. | M | Senior engineer | Months 2–3 | Open
ISS-22 | Raw internal error messages returned to API clients | API design | Low | Most routes return error.message verbatim (e.g., 'Task X is locked', storage errors). | Leaks internals; inconsistent, untranslated user-facing copy. | Minor information disclosure; confusing UX. | Stable {error:{code,message}} contract; map internals to safe messages; log details server-side. | S | Junior dev | Month 2 | Open

## Backlog Tickets
AAIS Engineering Backlog — next 3 months (P0=Wk1–2, P1=Wk3–4, P2=Month 2, P3=Month 3)
AAIS Technical Review — July 8, 2026 · companion to AAIS-Technical-Review-Report.docx
Ticket | Title | Description | Acceptance criteria | Priority | Effort | Suggested owner | Roadmap phase | Linked issue(s) | Status
T-01 | Rotate and re-home all credentials | Rotate every key/password in 'All API Keys.docx' at each provider; store in a password manager; delete the file; amend agents.md. | Old keys revoked and fail; file gone from disk; password-manager entries exist; no plaintext secrets in the folder besides documented .env.local. | P0 | S | Owner + junior | Weeks 1–2 | ISS-03 | Open
T-02 | Disable built-in demo accounts in production | Gate builtInLearnerTrialAccounts to non-production; rotate all configured trial passwords. | Bobie/12345 returns 401 on www.aais.site; dev login still works locally; unit test asserts production exclusion. | P0 | S | Junior dev | Weeks 1–2 | ISS-01 | Open
T-03 | Push repo to GitHub with protected main + working CI | Private repo, full history, main as protected default branch, Vercel Git integration. | CI green on a test PR; merge to main triggers Vercel deploy; direct CLI prod deploys stopped and documented. | P0 | S | Junior dev | Weeks 1–2 | ISS-02 | Open
T-04 | Minimal-disclosure readiness endpoint | Public GET returns {status} only; full report requires admin session or bearer token. | Anonymous fetch shows no release id/SHA/config; authorized fetch unchanged; tests cover both paths. | P0 | S | Junior dev | Weeks 1–2 | ISS-06 | Open
T-05 | Error tracking + uptime + cron alerts | Sentry for client and server with release tags; uptime monitor on /login; alert on cron flush failure. | Test error visible in Sentry; downtime and cron failure each trigger a notification to a human. | P0 | S | Junior dev | Weeks 1–2 | ISS-13 | Open
T-06 | Staging environment + documented env vars | Vercel preview environment + seeded Neon branch; .env.example covering local/staging/prod. | Staging URL loads with seed data; deploy-to-staging documented; prod secrets not reused where separable. | P0/P1 | M | Junior dev | Weeks 1–4 | ISS-05 | Open
T-07 | Verify backups and rehearse restore | Confirm Neon plan PITR/snapshot capability in writing; take snapshot; restore to a branch; document in OPERATIONS.md. | Written restore procedure with actual timings; snapshot schedule decided and enabled. | P0 | S | Junior + owner | Weeks 1–2 | ISS-05 | Open
T-08 | Optimistic locking on learner-session writes | Add version column; compare-and-swap update; single retry with merge-or-fail semantics. | Parallel-write race test (two simultaneous saves) loses no data; conflict metric logged. | P1 | M | Senior + junior | Weeks 3–4 | ISS-04 | Open
T-09 | Migration framework + baseline migration | Adopt node-pg-migrate (or equivalent); migration 001 formalizes the two existing tables; remove runtime CREATE TABLE. | A fresh database is built solely by migrations; CI runs migrations against a temp DB; runtime DDL deleted. | P1 | S | Junior dev | Weeks 3–4 | ISS-05 | Open
T-10 | Archive release-evidence pipeline | Move the 22 release/verify scripts and their tests to tools/release-legacy; keep one smoke:prod script (readiness + login + one learning write). | npm run ci time drops; test suite covers product + smoke only; README no longer references archived commands; one-page release checklist exists. | P1 | S | Junior dev | Weeks 3–4 | ISS-10 | Open
T-11 | Remove LangGraph dependency and misleading labels | Drop @langchain/langgraph; rename engine/runtime strings (e.g., aais-orchestrator-v1). | Dependency gone from package.json; no source or API response mentions langgraph; tests updated. | P1 | S | Junior dev | Weeks 3–4 | ISS-11 | Open
T-12 | Documentation set rewrite | 1-page README (what/run/deploy), ARCHITECTURE.md with real diagram, OPERATIONS.md (deploy/rollback/restore/incidents), CONTRIBUTING.md (branch/PR rules). | A new engineer completes local setup from README alone in under 30 minutes; old README archived. | P1 | S–M | Junior dev | Weeks 3–4 | ISS-20 | Open
T-13 | Playwright E2E suite in CI | Specs: login ok/fail; task select + artifact save + reload persistence; AI guide happy path + labeled fallback; teacher dashboard access + student blocked; cohort export. | Suite runs against PR preview URLs in CI; failure blocks merge. | P1→P2 | M | Junior dev | Weeks 3–8 | ISS-14 | Open
T-14 | Data model v2: users + events tables + backfill | Create users, aais_events (append-only), learner_task_state; backfill from JSONB blobs; dual-read for one release. | Rehearsed on staging from a prod snapshot; event counts reconcile with blobs; app reads from new tables; blob retained read-only until Month 3. | P2 | L | Senior + junior | Month 2 | ISS-04, ISS-15 | Open
T-15 | Invite-based registration + password reset | Admin invites by email (Resend); set-password flow; reset flow; admin user list page. | Full invite→login→reset cycle works on staging; env-JSON accounts kept only as break-glass; audit events for each step. | P2 | L | Senior + junior | Month 2 | ISS-08 | Open
T-16 | Individual teacher/admin accounts | Migrate static educator access to per-person users with roles. | Every human has own credentials; role changes logged; old educator env accounts removed. | P2 | S | Junior dev | Month 2 | ISS-08 | Open
T-17 | Durable rate limiting | Postgres or Upstash counters for login keyed by account + IP, with lockout and audit events. | Brute-force test across multiple serverless invocations receives 429; limits configurable by env. | P2 | S–M | Junior dev | Month 2 | ISS-07 | Open
T-18 | Frontend decomposition of learning page | Extract typed API client; split learning-page.tsx into TaskList, Workspace/Editor, GuideChat, ScaffoldPanel, ReflectionPanel, ExportMenu + hooks. | No file over 500 lines in the page tree; behavior identical (E2E green); component tests for 3 key components. | P2 | M–L | Junior (senior review) | Month 2 | ISS-09 | Open
T-19 | API error-code contract | Stable {error:{code,message}} response shape; internal messages logged server-side, not returned. | All routes conform; client shows friendly copy; contract documented for future endpoints. | P2 | S | Junior dev | Month 2 | ISS-22 | Open
T-20 | SQL cohort analytics | Replace load-everything aggregation with indexed SQL aggregates over aais_events; paginate learner drill-down. | Dashboard output matches old implementation on test data; p95 under 500ms with 500 simulated learners; memory flat. | P2/P3 | M | Senior engineer | Months 2–3 | ISS-15 | Open
T-21 | Learner profiles + rule-based recommendations | Profile aggregates (mastery, help dependency, reflection completeness); 5–8 explainable rules; recommendation API + UI card with reasons; teacher override logged as an event. | Scripted event fixtures produce expected recommendations with correct reasons; override works and is auditable; rules documented for teachers. | P3 | M–L | Senior + junior + owner | Month 3 | AI readiness | Open
T-22 | AI experience quality pass | Raise max tokens (~600); add 1 retry; true token streaming or staged honest progress; visible fallback labeling; per-student daily token budget. | p50 first token under 3s on staging; fallback clearly labeled in UI; per-student daily cost capped and logged. | P3 | M | Senior engineer | Month 3 | ISS-12, ISS-21 | Open

## 3-Month Roadmap
AAIS 3-Month Technical Recovery Roadmap
AAIS Technical Review — July 8, 2026 · companion to AAIS-Technical-Review-Report.docx
Phase | Timeframe | Goal | Key deliverables | Related tickets | Exit criteria
1. Stabilization & risk reduction | Weeks 1–2 | No anonymous access, no single point of loss, secrets contained, eyes on production | Keys rotated + docx deleted; demo accounts off in prod; GitHub repo + protected main + green CI; readiness endpoint locked down; Sentry + uptime + cron alerts; Neon backup verified + snapshot; staging environment created | T-01…T-07 | Demo login fails in prod; repo on GitHub with green CI; keys rotated; error dashboard live; staging URL exists
2. Architecture cleanup & documentation | Weeks 3–4 | Make the system safely changeable | Release pipeline archived + one smoke script; LangGraph dep/labels removed; docs set rewritten (README/ARCHITECTURE/OPERATIONS/CONTRIBUTING); migration framework + baseline migration; optimistic locking on writes; first 2 Playwright specs in CI | T-08…T-13 | New engineer sets up from docs alone; schema changes only via migrations; concurrent-write loss fixed at interim level
3. Core refactoring & feature foundation | Month 2 | Real accounts and a data layer that supports the product | Data model v2 (users, events, task state) + backfill; invite registration + password reset; individual staff accounts; frontend decomposition; durable rate limiting; API error contract; full E2E suite | T-13…T-19 | Users invitable with self-service reset; events in SQL with aggregates; learning page componentized; E2E on every PR
4. Hardening & controlled expansion | Month 3 | Pilot-ready: honest AI, explainable recommendations, privacy answered | Learner profiles + rule-based recommendations with teacher override; AI quality pass (tokens/retry/streaming/fallback labels/budgets); privacy baseline (inventory, retention, export/delete, consent, DPAs); accessibility + mobile pass; nonce CSP; load sanity test; controlled pilot with one class | T-20…T-22 + checklist | Pilot ran with no data loss or unauthorized access; recommendations explainable; privacy questions answerable in writing

## Readiness Checklist
Minimum Production-Readiness Checklist (safe to invite one real class)
AAIS Technical Review — July 8, 2026 · companion to AAIS-Technical-Review-Report.docx
Category | Item | Required before | Owner | Status
Security | Built-in demo credentials disabled in production (verified by failed login) | Week 2 | Junior dev | TODO
Security | All API keys/passwords rotated after removing 'All API Keys.docx'; secrets only in Vercel env + password manager | Week 2 | Owner | TODO
Security | Individual accounts for every human (no shared teacher/admin credentials) | Pilot | Junior dev | TODO
Security | Durable login rate limiting verified across serverless instances | Pilot | Junior dev | TODO
Security | Readiness/diagnostics endpoints require auth beyond bare status | Week 2 | Junior dev | TODO
Security | Dependency audit (npm audit / Dependabot) clean of critical vulnerabilities in CI | Month 2 | Junior dev | TODO
Data | Migration tool in place; zero runtime DDL | Month 2 | Junior dev | TODO
Data | Concurrent-write safety proven by a test (two parallel saves, nothing lost) | Month 2 | Senior | TODO
Data | Nightly snapshot or PITR confirmed on the Neon plan in writing | Week 2 | Owner | TODO
Data | Restore rehearsed end-to-end quarterly (documented, under 1 hour) | Pilot | Junior dev | TODO
Data | Per-user data export and deletion implemented and tested | Pilot | Senior | TODO
Deployment | Deploys only from Git (main) via CI; laptop deploys disabled | Week 2 | Junior dev | TODO
Deployment | Staging environment with seeded data; every change staged first | Week 4 | Junior dev | TODO
Deployment | One-step rollback documented and rehearsed (Vercel redeploy + snapshot) | Month 2 | Junior dev | TODO
Deployment | Environment variables documented in .env.example for local/staging/prod | Week 4 | Junior dev | TODO
Testing | CI gate: lint + type-check + unit + build on every PR | Week 2 | Junior dev | TODO
Testing | Playwright E2E on the 3 core flows against preview deploys | Month 2 | Junior dev | TODO
Testing | Regression test exists for every Critical/High issue fixed | Month 3 | Junior dev | TODO
Monitoring | Sentry receiving client + server errors with alerts to a named human | Week 2 | Junior dev | TODO
Monitoring | Uptime check on /login and a cron-failure alert | Week 2 | Junior dev | TODO
Monitoring | Weekly 15-minute dashboard review owned by a named person | Week 2 | Owner | TODO
Documentation | README no longer than 1 page: what it is, run locally, deploy | Week 4 | Junior dev | TODO
Documentation | ARCHITECTURE.md with the real diagram and the deliberate 'not yet' list | Week 4 | Junior dev | TODO
Documentation | OPERATIONS.md: deploy, rollback, restore, incident basics | Week 4 | Junior dev | TODO
Documentation | CONTRIBUTING.md: branch, PR, and review rules | Week 4 | Junior dev | TODO
UX | Loading and error states on every async action (especially the AI guide) | Pilot | Junior dev | TODO
UX | AI fallback/template responses visibly labeled | Pilot | Senior | TODO
UX | Keyboard + screen-reader pass on the 3 core screens; contrast fixes | Pilot | Designer | TODO
UX | Stated mobile policy (supported, or a graceful larger-screen message) | Pilot | Owner | TODO